## Timesheet
FATHOM / PostgresTool — Security Audit & Remediation
Engineer: | Dilip Patil |  | Week of: | May 18 – May 22, 2026
Project: | Backend security audit + 15-fix remediation |  | Total hours: | 40
Date | Day | Task ID | Task / Activity | Severity | Hours
2026-05-18 | Mon | AUDIT | Inventory codebase (989 source files) + scope security audit | — | 2
2026-05-18 |  | AUDIT | Read auth, middleware, route, and service layers; grep high-risk patterns | — | 3.5
2026-05-18 |  | AUDIT | Write findings report (16 items) with file:line refs and remediation notes | — | 2.5
2026-05-19 | Tue | FIX #1 | Delete mock SSO endpoints (/api/auth/sso/*) — anyone-as-admin login bug | Critical | 2
2026-05-19 |  | FIX #2 | Remove NEW_SCREENS RBAC bypass in issueSession (~80 hardcoded screens) | Critical | 1.5
2026-05-19 |  | FIX #3 | License signature: switch to crypto.timingSafeEqual + 128-bit truncation | High | 2
2026-05-19 |  | FIX #4 | Harden MongoDB TLS — gate tlsAllowInvalidCertificates behind env var | High | 1
2026-05-19 |  | REVIEW | Self-review Tue diffs; run node --check; commit checkpoint | — | 1.5
2026-05-20 | Wed | FIX #5 | MySQL EXPLAIN validation: add assertExplainSafe + mutation regex | High | 2.5
2026-05-20 |  | FIX #14 | Wrap PG EXPLAIN in READ ONLY txn + statement_timeout; MySQL exec-time hint | Medium | 1.5
2026-05-20 |  | FIX #6 | Forgot-password: add rate-limit + 250ms min response to flatten timing | High | 2
2026-05-20 |  | FIX #13 | Drop /\$\d+/ from INJECTION_BYPASS_PATTERNS (false-positive on $N) | Quality | 1
2026-05-20 |  | REVIEW | Run explainParsers + envValidation tests; add err.status → HTTP mapping | — | 1
2026-05-21 | Thu | FIX #7 | Unify bcrypt cost factors across server.js + userService (10 → 12) | Medium | 1
2026-05-21 |  | FIX #8 | Add buildEnforcePasswordChange middleware; wire into authenticate | Medium | 2
2026-05-21 |  | FIX #9 | Rewrite 59 catch-and-swallow sites to log WARN with method/path/error | Medium | 2.5
2026-05-21 |  | FIX #10 | Add trimMapToCap; bound csrfTokens, rateBuckets, strictBuckets, loginAttempts, apiKeyRateLimits | Medium | 2.5
2026-05-22 | Fri | FIX #11 | Reject legacy JWTs without sid claim (was warning-only) | Medium | 1
2026-05-22 |  | FIX #15 | Add radix to all parseInt(req.params.id) + parseInt(req.query.X) sites | Quality | 0.5
2026-05-22 |  | FIX #16 | Delete duplicate middleware/ipWhitelist.js (unused; canonical is ipAllowList) | Quality | 0.5
2026-05-22 |  | VERIFY | Strip 2,456 trailing NUL bytes from server.js (filesystem corruption) | — | 1
2026-05-22 |  | VERIFY | Reconstruct 4 truncated files via git baseline + Python re-apply | — | 2
2026-05-22 |  | VERIFY | Run full test suite (110 tests across 17 suites), smoke-import server.js | — | 1.5
2026-05-22 |  | REPORT | Write fix summary; map each change to audit finding; commit | — | 1.5
|  |  | Weekly total |  | 40

## Daily Summary
Daily hours summary
Date | Day | Focus | Hours
2026-05-18 | Mon | Full audit — inventory, review, findings report | 8
2026-05-19 | Tue | Critical & high fixes — SSO, RBAC, license, MongoDB TLS | 8
2026-05-20 | Wed | EXPLAIN hardening + forgot-password timing | 8
2026-05-21 | Thu | Auth middleware, error swallowing, in-memory caps | 8
2026-05-22 | Fri | Cleanup, file reconstruction, full verification | 8
|  | Weekly total | 40

## By Severity
Hours by severity
Severity | Count | Hours
Critical | 2 | 3.5
High | 4 | 7.5
Medium | 6 | 10.5
Quality | 3 | 2
Audit / Verify / Review | 9 | 16.5
Total | 24 | 40