FATHOM (PostgresTool)

Implementation Plan

Closing the gaps identified 2 June 2026

# 1. How to read this plan

This document turns the gap analysis (FATHOM_Gap_Analysis_2026-06-02.docx) into a sequenced engineering plan. Every task lists the files that need to change, a short code sketch where helpful, the regression test to add, and an explicit acceptance criterion. Tasks are grouped into three waves:

- Wave A — 0 to 30 days. Closes the highest-priority security and operational gaps and removes the most visible code-quality debt. Mostly small, parallelisable PRs.

- Wave B — 30 to 90 days. Closes the depth gap on query analytics versus pganalyze and Datadog DBM, finishes the TypeScript migration, and splits the runtime into web + worker tiers.

- Wave C — 90+ days. Strategic: managed agent, SOC2 Type II, query-rewrite workbench, docs site, engine-focus decision.

Each task is labelled with an estimate (S ≤ 2d, M 3–5d, L 1–2w, XL 2w+), the area it belongs to (FEAT / CODE / SEC / PERF), and a suggested owner role (BE / FE / SRE / SEC / FullStack).

# 2. Wave A — 0 to 30 days

| # | Task | Area | Size | Owner | Closes gap |
| --- | --- | --- | --- | --- | --- |
| A1 | Replace in-memory rate limiter with Redis-backed limiter | SEC | M | BE/SRE | Distributed rate-limit |
| A2 | Wire Dependabot + npm audit + pip-audit in CI | SEC | S | SEC | CVE scanning |
| A3 | Add Postgres wait-event sampler service + table | FEAT | L | BE | DBM parity (wait events) |
| A4 | Consolidate charting library and delete duplicate views | CODE | M | FE | Bundle size + UX |
| A5 | Document copilot history retention + add purge job | SEC | S | BE | GDPR/PII purge |
| A6 | Write docs/ARCHITECTURE.md (web vs worker split) | PERF | S | BE | Operational clarity |
| A7 | Remove .pristine and patch files; collapse V1/V2/V3 variants | CODE | S | FE | Code hygiene |
| A8 | Add SCIM token rotation UI + webhook | SEC | M | FullStack | Token lifecycle |

## A1. Distributed rate limiter (Redis-backed)

Current limiter (backend/middleware/rateLimiter.js, also a second inline copy at backend/server.js:730) keeps buckets in a per-process Map. With 2+ backend instances behind a load balancer the limit is multiplied by N. ioredis is already an optional dependency.

Files:

- backend/middleware/rateLimiter.js — replace in-memory Map with token-bucket implemented in Redis via Lua atomic script (EVAL). Keep the in-memory fallback when REDIS_URL is unset.

- backend/server.js:730 — delete the duplicate inline rateLimiter function; import the one from middleware/.

- backend/services/redisClient.js — NEW. Shared singleton ioredis client with lazy connect + reconnectOnError.

- backend/tests/rateLimiterRedis.test.js — NEW. Cover: first request passes, N+1 returns 429, second instance shares the count, fallback works when REDIS_URL is missing.

Code sketch — atomic Lua script:

-- KEYS[1] = bucket key, ARGV[1] = max, ARGV[2] = window ms, ARGV[3] = now local n = redis.call('INCR', KEYS[1]) if n == 1 then redis.call('PEXPIRE', KEYS[1], ARGV[2]) end if n > tonumber(ARGV[1]) then return {n, redis.call('PTTL', KEYS[1])} end return {n, -1}

Env: REDIS_URL (optional in dev, required in prod via .env.example update).

Acceptance: Two Node processes pointed at the same REDIS_URL share a single rate-limit budget; integration test passes; existing in-memory tests still pass with REDIS_URL unset.

## A2. Dependency CVE scanning in CI

Files:

- .github/dependabot.yml — NEW. Weekly schedule for npm (root, backend, frontend, sdk), pip (python/), gomod (sdk/go). Group dev-dependencies.

- .github/workflows/security.yml — MODIFY. Add jobs: npm-audit (--audit-level=high), pip-audit, govulncheck. Fail on HIGH+.

- .github/workflows/ci.yml — MODIFY. Add gosec on sdk/go and bandit on python/.

Code sketch — npm-audit job:

- name: npm audit (backend) working-directory: backend run: npm audit --omit=dev --audit-level=high

Acceptance: PRs with a HIGH CVE in production deps are blocked by CI. Dependabot opens automated PRs on a weekly cadence.

## A3. Postgres wait-event sampler

Largest analytics gap versus Datadog DBM and Percona PMM. Sample pg_stat_activity at 1 Hz (configurable), bucket by wait_event_type / wait_event, store in a time-series rollup, surface in the existing PerformanceTab.

Files:

- backend/services/waitEventSampler.js — NEW. Pollers per monitored Postgres connection. Same scheduling shape as syntheticMonitor.js (one in-flight per check, drop overlaps, absolute timeout).

- backend/db/migrations/0010_wait_events.sql — NEW. Two tables: wait_event_samples (raw, retained 24h) and wait_event_rollups_5m (1-week retention).

- backend/routes/observabilityRoutes.js — EXTEND. GET /observability/wait-events?connectionId&from&to&bucket=5m.

- frontend/src/components/views/monitoring/PerformanceTab.tsx — EXTEND. Stacked-area chart of wait classes (CPU, IO, Lock, IPC, Client, BufferPin, Activity).

- backend/services/retentionService.js — EXTEND. Add wait_event_* tables to the retention sweep.

- backend/tests/waitEventSampler.test.js — NEW. Mock pg_stat_activity rows; assert bucketing, drop-on-overlap, retention.

Schema sketch:

CREATE TABLE pgmonitoringtool.wait_event_samples ( connection_id uuid NOT NULL, sampled_at timestamptz NOT NULL, pid int NOT NULL, wait_event_type text, wait_event text, state text, query_id bigint ); CREATE INDEX ON pgmonitoringtool.wait_event_samples (connection_id, sampled_at DESC); CREATE TABLE pgmonitoringtool.wait_event_rollups_5m ( connection_id uuid NOT NULL, bucket_start timestamptz NOT NULL, wait_class text NOT NULL, sample_count int NOT NULL, PRIMARY KEY (connection_id, bucket_start, wait_class) );

Acceptance: Operator can open PerformanceTab on a Postgres connection and see a stacked-area chart of wait classes over the last hour; rollup table populates within 5 minutes of enabling; retention sweep prunes old samples.

## A4. Charting library consolidation

Both Highcharts (root package.json) and Recharts (frontend/package.json) are bundled. Plus d3 for custom viz. Pick Recharts (already deeper in views) and remove Highcharts unless a chart genuinely needs it.

Files:

- Run grep across frontend/src for highcharts imports → list every view that uses it.

- Rewrite each highcharts chart in Recharts. If one chart genuinely needs Highcharts (e.g., 3D / heatmap / waterfall), keep Highcharts but scope it via a dynamic import so it lands in its own chunk.

- package.json (root) — remove highcharts.

- frontend/package.json — remove highcharts and highcharts-react-official unless retained for one chunk.

Acceptance: vite build bundle visualizer shows highcharts gone or in a lazy chunk; no production view fails to render; CI passes.

## A5. Copilot history retention + purge

Conversation turns are redacted at write (services/copilotService.js, post-audit fix HIGH-4), but there is no documented TTL. PII risk if a user pastes a regulated identifier that the redactor does not catch.

Files:

- backend/services/copilotService.js — add purgeOldConversations(maxAgeDays = 30).

- backend/server.js — register node-cron job daily at 04:00 to call purgeOldConversations().

- backend/routes/copilotRoutes.js — DELETE /copilot/history/:id for user-initiated purge.

- backend/docs/COPILOT_RETENTION.md — NEW. Document the TTL, the manual purge endpoint, and the redaction matrix.

- frontend Copilot.tsx — add 'Delete this conversation' button.

Acceptance: Conversations older than 30 days are purged nightly; users can delete a thread on demand; behaviour documented.

## A6. Architecture doc

Even before splitting processes, write the target so reviewers can refuse new work in the web tier that belongs in a worker tier.

Files:

- backend/docs/ARCHITECTURE.md — NEW. Sections: process topology today, target topology (web tier vs worker tier vs python analytics), queue boundaries, scaling units, hot paths. Include a mermaid diagram.

Acceptance: Doc merged; linked from README; PR reviewers reference it.

## A7. Code hygiene

Files to delete or collapse:

- frontend/src/components/views/monitoring/OverviewTab.tsx.pristine — delete.

- fix-overview-tail.patch — delete (repo root).

- IndexesTab.tsx, IndexesTabV2.tsx, IndexesTabV3.tsx — pick the latest, rename to IndexesTab.tsx, delete the others. Same for CapacityPlanningTab/V2/V3.

- CONVERSION_SUMMARY.md and TYPESCRIPT_MIGRATION.md inside views/database/ — fold into a single backend/docs/MIGRATION_NOTES.md and delete the in-source copies.

Acceptance: git ls-files shows no .pristine, no V2/V3 duplicates, no patch files.

## A8. SCIM token rotation

MED-3 added expires_at, but rotation is manual. Add UI and a webhook so Okta/Azure AD can rotate on their schedule.

Files:

- backend/routes/scimRoutes.js — POST /scim/tokens/:id/rotate, returns new token once.

- frontend/src/pages/SsoSettings.tsx — UI to list, rotate, and revoke tokens with expiry banner < 14 days.

- backend/services/notifiers — email reminder 14d and 3d before expiry.

- backend/tests/scimAuth.test.js — extend to cover rotation.

Acceptance: Owner can rotate a SCIM token from the UI; old token rejected immediately; email sent on expiry windows.

# 3. Wave B — 30 to 90 days

| # | Task | Area | Size | Owner | Closes gap |
| --- | --- | --- | --- | --- | --- |
| B1 | Web + worker process split with Redis/NATS queue | PERF | L | SRE/BE | Horizontal scaling |
| B2 | Cluster-aware index advisor | FEAT | M | BE | pganalyze parity |
| B3 | Query-rewrite workbench (EXPLAIN A/B harness) | FEAT | L | FullStack | Workbook parity |
| B4 | Finish backend TypeScript migration | CODE | XL | BE | Type safety end-to-end |
| B5 | Shared Zod schemas + generated FE client | CODE | L | FullStack | Contract drift |
| B6 | Adapter capability negotiation layer | CODE | M | BE | Engine UI consistency |
| B7 | User-built dashboards (CustomDashboardTab fully wired) | FEAT | L | FullStack | Dashboard parity |
| B8 | Backup orchestration service (or remove the tab) | FEAT | L | BE | Feature truth |
| B9 | OTLP ingest behind a queue | PERF | M | SRE/BE | Trace burst handling |
| B10 | Field-level encryption for workbench/history | SEC | M | BE | PII at rest |

## B1. Web tier + worker tier split

Today server.js owns Express, ws, node-cron, alert engine, OTLP ingest, and synthetic checks. Split into:

- backend/server.js (web tier) — Express + ws only. Publishes jobs to the queue, never runs cron.

- backend/worker.js — NEW. Owns node-cron, alertService, syntheticMonitor, retentionService, auditExport, copilot history purge.

- backend/services/queue.js — NEW. Thin abstraction over BullMQ (Redis) with a fallback to in-process for dev.

- Procfile and railway.json — DECLARE two processes: web + worker. Vercel keeps web only.

- backend/scripts/doctor.js — extend to verify both tiers can talk to Redis.

Acceptance: npm run dev starts both tiers; killing the worker does not break the API; killing the API does not lose queued alerts (they replay on restart).

## B2. Cluster-aware index advisor

Today indexAdvisor.js reads one connection. pganalyze went cluster-aware in Feb 2026 — unify recommendations across primary + replicas.

Files:

- backend/services/indexAdvisor.js — accept a list of connectionIds belonging to the same cluster. Union missing-index recommendations, intersect unused-index recommendations (only mark unused if unused everywhere).

- backend/db/migrations/0011_clusters.sql — NEW. cluster_id on connections + cluster_members table.

- backend/routes/advisorRoutes.js — accept clusterId or fall back to single connectionId.

- frontend/src/components/views/database/IndexesTab.tsx — show 'unused on N/M servers' so the operator can see partial-cluster usage.

- backend/tests/indexAdvisor.test.js — extend with cluster fixtures (primary used, replica unused).

Acceptance: An index used only on a replica is no longer flagged unused; cluster membership editable in the UI; existing single-connection callers still work.

## B3. Query-rewrite workbench

Closes the pganalyze Workbooks gap. Operator picks a slow query, copilot suggests a rewrite, system runs EXPLAIN ANALYZE on both against a read-replica or a sandbox, surfaces a diff.

Files:

- backend/services/workbookService.js — NEW. createWorkbook(connectionId, baseQuery), addVariant(variantSql), runVariants(workbookId) -> EXPLAIN ANALYZE both, store result.

- backend/routes/workbookRoutes.js — NEW. Mounted under /workbench/workbooks. Reuses requireWorkspaceRole('editor').

- frontend/src/components/views/database/QueryOptimizerTab.tsx — EXTEND with a 'Compare variants' panel.

- DB: workbooks, workbook_variants, workbook_runs tables.

Important: enforce read-only or sandbox connection on variant execution — extend isSafeToRun used by copilot.

Acceptance: Operator can record baseline and 1+ variants of a query, run them against a chosen connection, and see plan/timing diffs side-by-side.

## B4. Finish backend TypeScript migration

Strategy: incremental. allowJs=true, checkJs=true; convert one module per PR starting with the highest-blast-radius files (auth, RBAC, db pool, error middleware), then routes, then services.

Files:

- backend/tsconfig.json — set strict, noImplicitAny, target ES2022, module NodeNext, allowJs, outDir build/.

- backend/types/ — promote to first-class @fathom/types package.

- Conversion order: db.js, middleware/authenticate.js, middleware/workspaceRbac.js, middleware/tenantIsolation.js, services/encryptionService.js, services/userService.js → then routes.

- Replace tsx loader with esbuild-register or compile-on-build via tsup for prod start.

Acceptance: npm run type-check passes with no errors; CI gate added; new files must be .ts.

## B5. Shared Zod schemas + generated FE client

Files:

- shared/contracts/ — NEW workspace. One file per route domain (alerts.ts, advisor.ts, copilot.ts, etc.) exporting Zod schemas for request/response.

- backend/middleware/validate.ts — NEW. validate(schema) middleware that 400s on mismatch.

- frontend/src/lib/api.ts — replace ad-hoc fetch with a typed client generated from the shared schemas.

- scripts/gen-openapi.mjs — emit OpenAPI from the Zod schemas via zod-to-openapi. Drop the result at sdk/openapi/fathom-sdk.yaml so the SDK stays in sync.

Acceptance: Renaming a field in shared/contracts/ breaks both FE and BE type-checks; OpenAPI file regenerates on build.

## B6. Adapter capability negotiation

Files:

- backend/services/dbAdapters/BaseAdapter.js (or .ts after B4) — add capabilities(): { explain, waitEvents, indexStats, replication, … }.

- Each adapter — override capabilities() with truthful answers.

- backend/routes/sessionRoutes.js — return capabilities in the session payload so the frontend can show/hide tabs without engine-name string checks.

- frontend/src/components/layout/* — drive tab visibility from capabilities, not from engine strings.

Acceptance: Adding a new adapter and declaring capabilities is enough to surface the right tabs; no FE changes required.

## B7. User-built dashboards

CustomDashboardTab.tsx exists but has no documented backend. Wire it to the metricsRegistry.

Files:

- backend/db/migrations/0012_dashboards.sql — dashboards, dashboard_panels, dashboard_shares.

- backend/routes/dashboardRoutes.js — CRUD + share. Per-workspace scoping; viewer can read, editor can edit.

- frontend/src/components/views/analytics/CustomDashboardTab.tsx — drag-to-add panel; bind to a metric from the registry; pick chart type, time range, group-by.

- frontend/src/components/shared/PanelRenderer.tsx — NEW. Single panel renderer used in fixed and custom dashboards.

Acceptance: Operator can compose a dashboard from 5 panels, save it, share read-only link inside the workspace, and reopen it intact.

## B8. Backup orchestration (or remove BackupRecoveryTab)

Pick one of two paths. Keeping the tab means committing to real orchestration; pulling it is honest and removes scope creep.

Files (build path):

- backend/services/backupService.js — NEW. Postgres path uses pgBackRest if present, falls back to pg_basebackup. MongoDB path uses mongodump. Jobs are queued via the B1 worker tier.

- backend/routes/backupRoutes.js — schedule, list, restore (restore behind a stronger role: owner).

- backend/db/migrations/0013_backups.sql — backup_schedules, backup_runs.

Files (cut path):

- Delete BackupRecoveryTab.tsx and its route entry. Document the cut in docs/CHANGELOG.md.

Acceptance: Either backups run end-to-end with a verified restore drill in CI, or the UI no longer advertises a capability that does not exist.

## B9. OTLP ingest behind a queue

Files:

- backend/routes/otlpTraceRoutes.js — replace synchronous insert with enqueue(jobName, spanBatch).

- backend/worker.js — consume 'otlp.ingest' queue at configurable concurrency.

- backend/services/otlpTraceService.js — split parse (cheap, in web) from normalize-and-insert (heavy, in worker).

- backend/docs/TRACING.md — update for the new shape and the queue depth metric.

Acceptance: p99 OTLP response < 50 ms at 1k spans/s burst; queue depth observable in the metrics registry; no spans lost across a worker restart.

## B10. Field-level encryption for sensitive history

Connection secrets are already encrypted via ENCRYPTION_KEY. Workbench saved queries and copilot history may contain literals with PII and are stored plaintext.

Files:

- backend/services/encryptionService.js — add encryptField(plaintext, context) / decryptField(ciphertext, context) AAD-bound to (workspace_id, row_id).

- backend/services/workbenchService.js — encrypt body on write, decrypt on read.

- backend/services/copilotService.js — same for conversation_turns.user_input.

- backend/db/migrations/0014_fieldcrypto.sql — convert columns to bytea; backfill in batches.

Acceptance: DB dump shows no plaintext user input from workbench or copilot; existing reads succeed transparently.

# 4. Wave C — 90+ days (strategic)

| # | Task | Area | Size | Owner | Closes gap |
| --- | --- | --- | --- | --- | --- |
| C1 | Managed agent (Go binary, OSS-licensed) | FEAT | XL | BE/Go | Productisation |
| C2 | SOC2 Type II evidence + auditor engagement | SEC | XL | SEC | Enterprise sales |
| C3 | Docs site (Mintlify/Docusaurus) | FEAT | M | DevRel/FE | Productisation |
| C4 | Engine focus decision + adapter tier policy | CODE | M | Eng lead | Maintenance cost |
| C5 | Proactive AI-driven RCA | FEAT | L | BE/ML | DBM parity |
| C6 | Log-based EXPLAIN capture (auto_explain ingest) | FEAT | L | BE | pganalyze parity |
| C7 | Public benchmark + load harness | PERF | L | SRE | Credibility |

## C1. Managed agent

A thin Go binary that auto-discovers local databases, samples wait events and pg_stat_statements, and forwards via the existing SDK protocol. Reuse sdk/go/ machinery for transport and batching.

- Repo: sdk/go/cmd/fathom-agent/ for the binary; sdk/go/agent/ for the collectors.

- Collectors: postgres (pg_stat_statements + pg_stat_activity), mysql (performance_schema), mongo (db.serverStatus / currentOp), host (cpu, memory, disk via gopsutil).

- Distribution: GitHub releases with signed binaries (cosign); install one-liner; SystemD unit; Docker image.

- Backend: extend /api/observabilityIngest to accept agent payloads with per-agent API keys; tie agent identity to a connection.

Acceptance: One-line install on a Linux host produces wait-event data in FATHOM within 60 seconds; auto-updates respect a configured channel.

## C2. SOC2 Type II

Checklist file exists (FATHOM_SOC2_Controls_Checklist.md). Gap is evidence collection and auditor selection.

- Pick a Type II auditor with SaaS experience (e.g., Prescient, Johanson, AssuranceLab) and a 6-month observation window.

- Adopt Vanta/Drata/SecureFrame to automate evidence (~80% of controls).

- Map remaining controls to in-tree implementations: workspaceRbac.js, auditService.js, encryptionService.js, sessionService.js, ipAllowList.js. Write a one-line reference per control.

- Quarterly access reviews; documented incident-response runbook; tabletop exercise.

Acceptance: Type II report (clean opinion) issued; bridge letter strategy in place.

## C3. Docs site

- Pick Mintlify (fast, hosted) or Docusaurus (OSS) — Mintlify recommended for time-to-first-page.

- Ingest backend/docs/*.md and sdk/*/README.md as starting content.

- Add Getting Started, Connections per engine, Alerts, SSO/SCIM, SDKs, API reference (auto-generated from B5's OpenAPI).

Acceptance: docs.fathom.dev (or chosen domain) live; in-app 'Docs' links route there.

## C4. Engine focus decision

Maintaining 14 adapters at depth is expensive. Recommendation: tier them.

- Tier 1 (deep): Postgres, MySQL, MongoDB — full advisors, wait events, EXPLAIN, indexes, schema diff.

- Tier 2 (operational): Redis, MSSQL, Elasticsearch — health, connections, top queries; no advisor.

- Tier 3 (read-only support): BigQuery, DynamoDB, Cassandra, Oracle, Snowflake, Redshift — connection and basic stats only.

- Communicate the tier in UI and docs; cap roadmap scope by tier.

Acceptance: Public tier matrix; engineering backlog gated by tier.

## C5. Proactive AI-driven RCA

- On every fired alert, assemble: recent wait-event burst, top-N queries by load, recent OTLP traces matching the affected service, recent deploys.

- Pass to the existing copilot RCA narrative path; cache by (alert_id, signature) to keep LLM cost bounded.

- Surface as 'Probable cause' on the alert detail page; thumbs-up/down feedback feeds back into prompt selection.

## C6. auto_explain ingest

- Backend ingest endpoint for parsed auto_explain log lines; PII scrubber (reuse copilot redact()).

- Frontend: surface 'plan in production' alongside 'plan from EXPLAIN now' so operators see what actually happened, not what would happen.

## C7. Public benchmark + load harness

- k6 or vegeta scenarios for OTLP ingest, alert engine, dashboard reads. Targets: 5k spans/s, 200 alerts/min, p95 < 250 ms dashboard read.

- Publish numbers in docs and run weekly in CI.

# 5. Sequencing and dependencies

Critical path: A1 (Redis) → B1 (web/worker split) → B9 (OTLP queue) and C1 (agent). A2 and A7 are independent and can ship in parallel from day one. A3 (wait-event sampler) feeds B2 and C5. B4 (TypeScript) and B5 (shared schemas) should be sequenced before B6, B7 to avoid converting newly-written JS modules a second time.

| Task | Blocked by | Notes |
| --- | --- | --- |
| A1 Redis | — | Unlocks B1, B9, C1; safe to ship first because dev fallback preserves single-process workflow. |
| A2 CI scans | — | Independent; ship now to start collecting baseline CVE state. |
| A3 Wait events | — | Feeds B2 (cluster-aware advisor decisions) and C5 (RCA context). |
| A4 Charts | — | Pure FE; can land in any week. |
| A5 Copilot TTL | — | Independent. |
| A6 Architecture doc | — | Soft prerequisite for B1 review. |
| A7 Hygiene | — | Independent; encourage as warm-up PRs. |
| A8 SCIM rotation | — | Independent. |
| B1 Web/worker | A1 | Blocks B9; enables B8 (backup jobs) and C5 (alert-time context). |
| B2 Cluster advisor | A3 | Wait-event signal sharpens 'unused' decisions. |
| B3 Workbench | B5 (recommended) | Easier to type the new endpoints after shared schemas exist. |
| B4 TS migration | — | Run in parallel with everything; mandates new files in TS. |
| B5 Shared Zod | B4 partial | Best done once auth/db are TS. |
| B6 Capabilities | B4 | Type-safe negotiation is much cleaner. |
| B7 Dashboards | B5 | Needs typed metrics contract. |
| B8 Backup | B1 | Long-running jobs belong in the worker tier. |
| B9 OTLP queue | A1, B1 | Reuses queue infra. |
| B10 Field crypto | — | Can ship any time; migration must batch. |
| C1 Agent | A1, A3, B5 | Agent forwards wait-event + query data via typed contract. |
| C2 SOC2 | — | Multi-month track in parallel. |
| C3 Docs site | B5 | OpenAPI feeds the API reference. |
| C4 Engine focus | — | Policy decision; do early in C. |
| C5 RCA | A3, B1 | Worker pulls context; sampler provides wait-event burst. |
| C6 auto_explain | B9 | Same ingest plumbing. |
| C7 Benchmark | B1, B9 | Meaningful numbers require the split runtime. |

# 6. Risks and mitigations

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Worker-tier complexity blocks delivery | B1 is the single largest engineering change. Ship behind a feature flag; keep server.js capable of running both roles in dev (one process) so local dev stays simple. | Phased rollout |
| Redis becomes a single point of failure | Use a managed Redis with HA (Upstash, Elasticache, Railway Pro). Document failure modes in ARCHITECTURE.md. | Managed HA |
| TypeScript migration drags | Time-box modules; allow .js to coexist; gate only new files on TS. Pair-program the auth/db conversion since it touches everything. | Time-boxed sprints |
| Agent (C1) duplicates SDK scope | Reuse sdk/go internals; agent is a thin wrapper, not a parallel codebase. Single shared transport module. | Code reuse |
| SOC2 evidence gaps stall audit | Adopt Vanta/Drata before observation window opens; quarterly access review automated. | Compliance tooling |
| Engine-tier downgrade upsets users | Survey active connections per engine before announcing; grandfather existing Tier-3 connections; announce 6 months in advance. | Data-driven decision |
| Wait-event sampling adds DB load | Default 1 Hz with adaptive backoff under load (pause sampling if pg_stat_activity contention rises). Document overhead numbers. | Adaptive sampling |

# 7. Success metrics

- Security: zero open HIGH+ CVEs in production deps for 30 consecutive days; SOC2 Type II report issued.

- Performance: OTLP ingest p99 < 50 ms at 1k spans/s; alert engine median dispatch < 2 s; dashboard read p95 < 250 ms.

- Code quality: 100% of new backend files in TS; zero .pristine / V2 / V3 duplicates; bundle size for /app route under 600 KB gzipped.

- Features: wait-event chart shipped in PerformanceTab; query-rewrite workbook in production; agent installs counted weekly.

- Product: SOC2 Type II; docs site live; engine tier matrix published; first customer signed under enterprise contract.

# 8. Appendix — file map by task

New files (greenfield):

- backend/services/redisClient.js, queue.js, waitEventSampler.js, workbookService.js, backupService.js

- backend/worker.js, backend/routes/workbookRoutes.js, backend/routes/dashboardRoutes.js, backend/routes/backupRoutes.js

- backend/db/migrations/0010_wait_events.sql, 0011_clusters.sql, 0012_dashboards.sql, 0013_backups.sql, 0014_fieldcrypto.sql

- backend/docs/ARCHITECTURE.md, COPILOT_RETENTION.md, MIGRATION_NOTES.md

- shared/contracts/ workspace with one file per route domain

- sdk/go/cmd/fathom-agent/, sdk/go/agent/

- .github/dependabot.yml, scripts/gen-openapi.mjs

Modified hotspots:

- backend/server.js (rate limiter dedup, queue producer, drop cron)

- backend/middleware/rateLimiter.js (Redis backend)

- backend/services/indexAdvisor.js (cluster aware), encryptionService.js (field crypto), copilotService.js (TTL, RCA), otlpTraceService.js (split parse / insert)

- backend/routes/otlpTraceRoutes.js, advisorRoutes.js, scimRoutes.js, copilotRoutes.js, observabilityRoutes.js

- frontend/src/components/views/monitoring/PerformanceTab.tsx, database/IndexesTab.tsx, database/QueryOptimizerTab.tsx, analytics/CustomDashboardTab.tsx, layout/* (capabilities driven)

- frontend/src/pages/SsoSettings.tsx, lib/api.ts

- .github/workflows/security.yml, ci.yml

End of plan. See FATHOM_Gap_Analysis_2026-06-02.docx for the underlying gap rationale.